## FY26 Q3 Execution
FY26 Q3 Execution Report — Operation and Maintenance (O&M)
Demonstration Directorate · Cumulative fiscal year to date through 30 June 2026 · Dollars in thousands ($K)
SYNTHETIC DEMONSTRATION DATA — not real NSA, DoD, vendor, personnel or program information
Code | Program / activity | FY26 annual plan | Q3 obligation plan | Obligations | Obligation variance | Obligation variance % | Q3 expenditure plan | Expenditures | Expenditure variance | Expenditure variance % | Remarks
SYN-101 | Workforce Training & Certification | 4800 | 3600 | 3540 | -60 | -1.667% | 2900 | 2860 | -40 | -1.379%
SYN-102 | Enterprise Help Desk Services | 7200 | 6000 | 1200 | -4800 | -80% | 2000 | 700 | -1300 | -65% | Follow-on contract award slipped from Mar to Aug (source selection delay); incumbent continuing on reduced-scope bridge.
SYN-103 | Facilities Sustainment | 4800 | 3600 | 5400 | 1800 | 50% | 2700 | 3050 | 350 | 12.96% | Received $1,800K on 14 May via below-threshold reprogramming for roof and HVAC repairs; spend plan not yet rebaselined.
SYN-104 | Utilities | 5200 | 3900 | 3960 | 60 | 1.538% | 3900 | 3880 | -20 | -0.5128% | Seasonal cooling load slightly above estimate.
SYN-105 | Network Operations Support | 9600 | 7200 | 7050 | -150 | -2.083% | 5800 | 5700 | -100 | -1.724% | Two contractor positions vacant in May.
SYN-106 | Data Center Operations | 6400 | 4800 | 4860 | 60 | 1.25% | 3800 | 3760 | -40 | -1.053%
SYN-107 | End-User Device Refresh | 2800 | 2100 | 5200 | 3100 | 147.6% | 1600 | 2050 | 450 | 28.12% | One-time purchase of 1,150 replacement workstations (end of life), approved by resource board 2 Jun; unit cost below expense/investment threshold.
SYN-108 | Software Licenses & Maintenance | 3800 | 2500 | 3750 | 1250 | 50% | 2000 | 2010 | 10 | 0.5% | Document SYN-26-0447 ($1,250K annual license renewal) posted 12 May and again 13 May.
SYN-109 | Mission Support Services | 7200 | 5400 | 5360 | -40 | -0.7407% | 4100 | 1500 | -2600 | -63.41% | Task order obligated on schedule; contractor invoices for Apr–Jun not yet received.
SYN-110 | Cybersecurity Tools Sustainment | 5600 | 4200 | 4150 | -50 | -1.19% | 3300 | 3240 | -60 | -1.818%
SYN-111 | Travel — Mission | 1600 | 1150 | 1090 | -60 | -5.217% | 1050 | 990 | -60 | -5.714%
SYN-112 | Travel — Training | 600 | 420 | 400 | -20 | -4.762% | 380 | 360 | -20 | -5.263%
SYN-113 | Supplies & Materials | 1200 | 900 | 930 | 30 | 3.333% | 760 | 780 | 20 | 2.632%
SYN-114 | Printing & Reproduction | 300 | 225 | 210 | -15 | -6.667% | 200 | 190 | -10 | -5%
SYN-115 | Telecommunications Services | 4000 | 3000 | 3040 | 40 | 1.333% | 2700 | 2690 | -10 | -0.3704%
SYN-116 | Equipment Maintenance | 2400 | 1800 | 1760 | -40 | -2.222% | 1350 | 1330 | -20 | -1.481%
SYN-117 | Records Management | 900 | 675 | 690 | 15 | 2.222% | 600 | 610 | 10 | 1.667%
SYN-118 | Logistics & Warehousing | 2000 | 1500 | 1470 | -30 | -2% | 1200 | 1180 | -20 | -1.667%
SYN-119 | Security Operations Support | 3200 | 2400 | 2430 | 30 | 1.25% | 1900 | 1920 | 20 | 1.053%
SYN-120 | Analytic Tools & Data Services | 4400 | 3300 | 3180 | -120 | -3.636% | 2500 | 2430 | -70 | -2.8% | Annual license true-up deferred to Jul.
SYN-121 | Studies & Analysis | 1800 | 1000 | 960 | -40 | -4% | 600 | 560 | -40 | -6.667%
SYN-122 | Financial Systems Support | 2600 | 1950 | 1970 | 20 | 1.026% | 1500 | 1490 | -10 | -0.6667%
SYN-123 | Professional Development & Conferences | 500 | 300 | 280 | -20 | -6.667% | 260 | 240 | -20 | -7.692%
SYN-124 | Environmental & Safety Compliance | 1400 | 1050 | 1040 | -10 | -0.9524% | 900 | 890 | -10 | -1.111%
SYN-125 | Transportation of Things | 700 | 525 | 540 | 15 | 2.857% | 460 | 470 | 10 | 2.174%
| Total | 85000 | 63495 | 64460 | 965 | 1.52% | 48460 | 44880 | -3580 | -7.388%
Notes: Variance = actual minus plan; negative means below plan. Plan = original FY26 spend plan, cumulative through Q3. Expenditures = disbursements recorded through 30 June.
Prepared for training use only.