FY26 Q3 Execution Report — Operation and Maintenance (O&M)

Demonstration Directorate · Cumulative fiscal year to date through 30 June 2026 · Dollars in thousands ($K)

SYNTHETIC DEMONSTRATION DATA — not real NSA, DoD, vendor, personnel or program information

| Code | Program / activity | FY26 annual plan | Q3 obligation plan | Obligations | Obligation variance | Obligation variance % | Q3 expenditure plan | Expenditures | Expenditure variance | Expenditure variance % | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SYN-101 | Workforce Training & Certification | 4,800 | 3,600 | 3,540 | -60 | -1.7% | 2,900 | 2,860 | -40 | -1.4% |  |
| SYN-102 | Enterprise Help Desk Services | 7,200 | 6,000 | 1,200 | -4,800 | -80.0% | 2,000 | 700 | -1,300 | -65.0% | Follow-on contract award slipped from Mar to Aug (source selection delay); incumbent continuing on reduced-scope bridge. |
| SYN-103 | Facilities Sustainment | 4,800 | 3,600 | 5,400 | 1,800 | 50.0% | 2,700 | 3,050 | 350 | 13.0% | Received $1,800K on 14 May via below-threshold reprogramming for roof and HVAC repairs; spend plan not yet rebaselined. |
| SYN-104 | Utilities | 5,200 | 3,900 | 3,960 | 60 | 1.5% | 3,900 | 3,880 | -20 | -0.5% | Seasonal cooling load slightly above estimate. |
| SYN-105 | Network Operations Support | 9,600 | 7,200 | 7,050 | -150 | -2.1% | 5,800 | 5,700 | -100 | -1.7% | Two contractor positions vacant in May. |
| SYN-106 | Data Center Operations | 6,400 | 4,800 | 4,860 | 60 | 1.2% | 3,800 | 3,760 | -40 | -1.1% |  |
| SYN-107 | End-User Device Refresh | 2,800 | 2,100 | 5,200 | 3,100 | 147.6% | 1,600 | 2,050 | 450 | 28.1% |  |
| SYN-108 | Software Licenses & Maintenance | 3,800 | 2,500 | 3,750 | 1,250 | 50.0% | 2,000 | 2,010 | 10 | 0.5% | Document SYN-26-0447 ($1,250K annual license renewal) posted 12 May and again 13 May. |
| SYN-109 | Mission Support Services | 7,200 | 5,400 | 5,360 | -40 | -0.7% | 4,100 | 1,500 | -2,600 | -63.4% |  |
| SYN-110 | Cybersecurity Tools Sustainment | 5,600 | 4,200 | 4,150 | -50 | -1.2% | 3,300 | 3,240 | -60 | -1.8% |  |
| SYN-111 | Travel — Mission | 1,600 | 1,150 | 1,090 | -60 | -5.2% | 1,050 | 990 | -60 | -5.7% |  |
| SYN-112 | Travel — Training | 600 | 420 | 400 | -20 | -4.8% | 380 | 360 | -20 | -5.3% |  |
| SYN-113 | Supplies & Materials | 1,200 | 900 | 930 | 30 | 3.3% | 760 | 780 | 20 | 2.6% |  |
| SYN-114 | Printing & Reproduction | 300 | 225 | 210 | -15 | -6.7% | 200 | 190 | -10 | -5.0% |  |
| SYN-115 | Telecommunications Services | 4,000 | 3,000 | 3,040 | 40 | 1.3% | 2,700 | 2,690 | -10 | -0.4% |  |
| SYN-116 | Equipment Maintenance | 2,400 | 1,800 | 1,760 | -40 | -2.2% | 1,350 | 1,330 | -20 | -1.5% |  |
| SYN-117 | Records Management | 900 | 675 | 690 | 15 | 2.2% | 600 | 610 | 10 | 1.7% |  |
| SYN-118 | Logistics & Warehousing | 2,000 | 1,500 | 1,470 | -30 | -2.0% | 1,200 | 1,180 | -20 | -1.7% |  |
| SYN-119 | Security Operations Support | 3,200 | 2,400 | 2,430 | 30 | 1.2% | 1,900 | 1,920 | 20 | 1.1% |  |
| SYN-120 | Analytic Tools & Data Services | 4,400 | 3,300 | 3,180 | -120 | -3.6% | 2,500 | 2,430 | -70 | -2.8% | Annual license true-up deferred to Jul. |
| SYN-121 | Studies & Analysis | 1,800 | 1,000 | 960 | -40 | -4.0% | 600 | 560 | -40 | -6.7% |  |
| SYN-122 | Financial Systems Support | 2,600 | 1,950 | 1,970 | 20 | 1.0% | 1,500 | 1,490 | -10 | -0.7% |  |
| SYN-123 | Professional Development & Conferences | 500 | 300 | 280 | -20 | -6.7% | 260 | 240 | -20 | -7.7% |  |
| SYN-124 | Environmental & Safety Compliance | 1,400 | 1,050 | 1,040 | -10 | -1.0% | 900 | 890 | -10 | -1.1% |  |
| SYN-125 | Transportation of Things | 700 | 525 | 540 | 15 | 2.9% | 460 | 470 | 10 | 2.2% |  |
|  | Total | 85,000 | 63,495 | 64,460 | 965 | 1.5% | 48,460 | 44,880 | -3,580 | -7.4% |  |

Notes: Variance = actual minus plan; negative means below plan. Plan = original FY26 spend plan, cumulative through Q3. Expenditures = disbursements recorded through 30 June.

Prepared for training use only.